NEXUS TECH SOLUTIONS

Enterprise Software Development

COST ESTIMATION & INFRASTRUCTURE PLAN

Production-Grade SaaS Platform Development

CONFIDENTIAL

Document Type: Cost Estimation & Infrastructure Plan

Prepared By: Nexus Tech Solutions

Document Date: May 15, 2026

Valid Until: June 15, 2026 (30 Days)

© 2026 Nexus Tech Solutions. All Rights Reserved. This document contains confidential information intended solely for the recipient. Unauthorized reproduction or distribution is prohibited.

# 1. Executive Overview

## 1.1 Project Description

This document provides a comprehensive cost estimation and infrastructure plan for the development of a production-grade SaaS platform. The platform is designed to serve enterprise clients with scalable, secure, and high-performance solutions. Our approach emphasizes architectural excellence, long-term maintainability, and seamless scalability to support growth from startup phase to enterprise scale.

## 1.2 Technology Stack

- Frontend: React.js 18+ with TypeScript, Redux Toolkit, Next.js for SSR

- Backend: Node.js with Express.js, RESTful & GraphQL APIs

- Database: PostgreSQL 15+ for relational data, Redis for caching

- Authentication: JWT, OAuth 2.0, SAML 2.0 support

- Testing: Jest, Mocha, Cypress, Selenium for E2E testing

- DevOps: Docker, Kubernetes, CI/CD pipelines (GitHub Actions)

## 1.3 Infrastructure Stack

- Cloud Platform: AWS (EC2, RDS, S3, CloudFront, Lambda)

- Container Orchestration: Kubernetes (EKS) for auto-scaling

- Monitoring & Logging: DataDog, CloudWatch, ELK Stack

- CDN: CloudFront for global content distribution

- Security: SSL/TLS, WAF, DDoS protection, encryption at rest

## 1.4 Architecture Highlights

- Microservices architecture for independent scaling

- API-first design enabling seamless integrations

- 99.9% uptime SLA with multi-region deployment

- Horizontal scaling capability for unlimited growth

- Production-grade security and compliance (GDPR, SOC2)

- Automated testing and continuous deployment pipeline

## 1.5 Document Purpose

This Cost Estimation & Infrastructure Plan outlines the complete financial investment required for developing a production-ready SaaS platform. It includes detailed cost breakdowns by component, a structured sprint-based payment schedule, clear delineation of included deliverables versus client responsibilities, and infrastructure requirements. This document serves as the basis for project agreement and resource allocation.

# 2. Total Development Cost

## 2.1 Cost Summary

| Cost Category | Percentage | Amount (₹) |
| --- | --- | --- |
| Architecture & Design | 12% | ₹30,00,000 |
| Frontend Development | 28% | ₹70,00,000 |
| Backend Development | 32% | ₹80,00,000 |
| Testing & QA | 16% | ₹40,00,000 |
| Deployment & Documentation | 12% | ₹30,00,000 |
| TOTAL DEVELOPMENT COST | 100% | ₹2,50,00,000 |

## 2.2 Detailed Cost Breakdown

| Component | Description | Days | Cost (₹) |
| --- | --- | --- | --- |
| System Architecture | Design & specifications | 15 | ₹15,00,000 |
| Database Design | Schema & optimization | 10 | ₹10,00,000 |
| Frontend Components | React components & UI | 45 | ₹45,00,000 |
| State Management | Redux, API integration | 25 | ₹25,00,000 |
| Backend APIs | REST/GraphQL endpoints | 50 | ₹50,00,000 |
| Authentication & Auth | JWT, OAuth, SAML | 20 | ₹20,00,000 |
| Automated Testing | Unit, Integration, E2E | 30 | ₹30,00,000 |
| Performance Opt. | Caching, Load testing | 15 | ₹15,00,000 |
| DevOps & Deployment | Docker, K8s, CI/CD | 20 | ₹20,00,000 |
| Documentation | API, deployment guides | 10 | ₹10,00,000 |

## 2.3 What's Included

- Complete frontend and backend development

- Database design, optimization, and administration setup

- Automated testing suite (unit, integration, E2E tests)

- Security implementation (authentication, authorization, encryption)

- Code documentation and technical specifications

- Performance optimization and code review

- 3 months post-launch support and bug fixes

- Developer handoff documentation and knowledge transfer

## 2.4 Exclusions

- Infrastructure Costs: Hosting, CDN, databases (See Section 3)

- Third-Party APIs: Payment gateways, email services, SMS, analytics

- Licenses & Tools: SSL certificates, monitoring tools, design software

- Maintenance Beyond 3 Months: Billed separately at ₹1,50,000/month

- Additional Features: Estimated separately based on complexity

## 2.5 Monthly Infrastructure Costs (Post-Launch)

Estimated: ₹80,000 - ₹1,20,000/month

Includes AWS hosting, CDN, monitoring, database backups, and security tools. Exact costs vary based on user load and data volume.

# 3. Sprint-Based Payment Schedule

The project is structured into 6 development sprints over 24 weeks. Each sprint concludes with deliverables and corresponding payment milestone. This approach provides transparency, risk mitigation, and regular progress checkpoints.

| Sprint | Timeline | Key Deliverables | Payment | Cumulative |
| --- | --- | --- | --- | --- |
| Initial | Day 1 | Agreement signing & deposit | ₹15,00,000 | ₹15,00,000 |
| 1 | W1-W4 | Architecture, Design, DB Schema | ₹40,00,000 | ₹55,00,000 |
| 2 | W5-W8 | Frontend components & APIs | ₹40,00,000 | ₹95,00,000 |
| 3 | W9-W12 | Business logic & integrations | ₹40,00,000 | ₹1,35,00,000 |
| 4 | W13-W16 | Complete development & testing | ₹35,00,000 | ₹1,70,00,000 |
| 5 | W17-W20 | QA, optimization & documentation | ₹25,00,000 | ₹1,95,00,000 |
| 6 | W21-W24 | Deployment & launch support | ₹10,00,000 | ₹2,05,00,000 |
|  |  |  | Final | ₹2,50,00,000 |

## Payment Terms

- Initial Deposit: ₹15,00,000 (30%) due upon agreement signing

- Sprint Payments: Due within 7 days of sprint completion

- Final Payment: ₹10,00,000 upon production deployment

- Payment Methods: Bank transfer, cheque, or wire transfer

- Late Payment: 1.5% monthly interest on overdue amounts

## Sprint Details

### Sprint 1: Requirements, Design & Architecture (Weeks 1-4)

- Requirements finalization and technical specifications

- System architecture design and database schema

- Infrastructure setup and CI/CD pipeline

### Sprint 2-5: Core Development Sprints

- Frontend component development and UI implementation

- Backend API endpoints and business logic

- Database integration and testing

### Sprint 6: Testing, Optimization & Deployment

- Comprehensive QA and security testing

- Performance optimization and load testing

- Production deployment and launch support

# 4. Included vs Client Responsibility

| INCLUDED IN DEVELOPMENT COST | CLIENT RESPONSIBILITY |
| --- | --- |
| - Complete frontend development | - Provide detailed requirements |
| - Complete backend development | - Timely feedback & approvals |
| - Database design & optimization | - Arrange AWS hosting & infrastructure |
| - Automated testing (unit, integration) | - Procure API keys & third-party services |
| - Security implementation | - Provide domain & SSL certificates |
| - Code review & quality assurance | - Participate in UAT |
| - Performance optimization | - Provide test data & test users |
| - CI/CD pipeline setup | - Configure monitoring tools |
| - Comprehensive documentation | - Pay all infrastructure & API costs |
| - 3 months post-launch support | - Regular status reviews |

## Client Responsibilities - Detailed

### 4.1 Content & Requirements

- Provide detailed functional and non-functional requirements

- Furnish all content, copy, and marketing materials

- Provide branding guidelines, logos, and design assets

### 4.2 Timely Feedback & Approvals

- Review sprint deliverables and provide feedback within 5 business days

- Approve design mockups before development

- Sign off on requirements and architectural decisions

### 4.3 Infrastructure & External Services

- Arrange and pay for hosting infrastructure (AWS, etc.)

- Procure third-party API keys (payment gateway, SMS, email)

- Provide SSL certificates and domain management

- Configure monitoring and analytics tools

### 4.4 Data & Testing

- Prepare test data and user accounts for QA

- Provide access to production environment credentials

- Participate in UAT and provide timely feedback

## Nexus Tech Responsibilities - Detailed

### 4.5 Development Excellence

- Deliver production-grade code following industry standards

- Implement comprehensive automated testing (80%+ code coverage)

- Conduct code reviews and security audits

- Optimize performance and ensure scalability

### 4.6 Security & Compliance

- Implement industry-standard security practices

- Ensure GDPR and data protection compliance

- Conduct penetration testing and vulnerability assessment

- Implement encryption and secure data handling

### 4.7 Documentation & Support

- Provide comprehensive API documentation

- Create deployment and maintenance guides

- Deliver developer handoff documentation

- Provide 3 months of post-launch support

# 5. Future Feature Development

Features not included in the current scope will be estimated separately following the completion of this project. Additional feature development will be priced based on complexity, timeline, and resource requirements.

## 5.1 Feature Estimation Process

- Client submits detailed feature requirements and business context

- Technical analysis and effort estimation (3-5 business days)

- Cost proposal and timeline provided to client

- Upon approval, project initiation with new sprint cycle

## 5.2 Pricing Factors for Additional Features

- Complexity Level: Simple (UI), Moderate (Business Logic), Complex (Integration)

- Timeline: Longer timelines allow better optimization and lower costs

- Integration Requirements: Third-party APIs or legacy system integration

- Testing Scope: Comprehensive QA or focused testing

- Resource Allocation: Team size and seniority

## 5.3 Maintenance & Support Pricing

- Post-Launch (3 Months): Included in development cost

- Ongoing Support: ₹1,50,000/month (40 hours/month) or ₹3,75,000/month (120 hours/month)

- Feature Updates: Hourly rate ₹2,500/hour

- Emergency Support: ₹1,00,000/incident or retainer-based

# 6. General Terms & Conditions

## 6.1 Project Timeline

- Total Duration: 24 weeks (6 sprints of 4 weeks each)

- Delays caused by client (content, approvals): Extended timeline

- Delays from our side: Proportional time extension

## 6.2 Intellectual Property

- Client receives full IP ownership upon final payment

- Nexus Tech retains rights to use methodology and reusable components

- All third-party libraries and tools retain their original licenses

## 6.3 Limitations & Disclaimers

- This estimate is valid for 30 days from the document date

- Scope changes may affect timeline and costs

- Client responsible for securing necessary licenses and approvals

- Force majeure events may impact delivery

AUTHORIZATION & ACCEPTANCE

By signing below, both parties agree to the terms, conditions, cost structure, and timeline outlined in this Cost Estimation & Infrastructure Plan. This document forms the basis of the development agreement.

Client Name: ________________________________     Date: _______________

Authorized Signature: ________________________________

Title/Position: ________________________________

FOR NEXUS TECH SOLUTIONS

Project Manager: ________________________________     Date: _______________

Authorized Signature: ________________________________

NEXUS TECH SOLUTIONS

Enterprise Software Development | www.nexustech.com

Email: enterprise@nexustech.com | Phone: +91-XX-XXXX-XXXX